## project-management
Project Management
Phase I
Name | Person | Priority | Status | Timeline - Start | Timeline - End | Dependency | Activity Node Name | Predecessor | Duration | Cost/Day | Total Cost | Actual Complete | Incurred Cost | Activity Node | ACWP | BCWP | BCWS | Today-End | Early Start | Early Finish | Late Start | Late Finish | Slack | Critical Path | Is Slack == 0?
Requirement Analysis | Shreya Shetty, Shruti Shetty | High | Done | 2022-08-31 | 2022-09-04 |  | A |  | 4 | 500 | 2000 | 100 | 2000 | A | 2000 | 2000 | 2000 | 4 | 0 | 4 | 0 | 4 | 0 | Yes | Yes
Defining Problem Statement | Shreya Shetty | High | Done | 2022-09-05 | 2022-09-06 | Requirement Analysis | B | A | 1 | 600 | 600 | 100 | 500 | B | 500 | 600 | 600 | 1 | 4 | 5 | 4 | 5 | 0 | Yes | Yes
Defining Objectives and Features | Shruti Shetty | High | Done | 2022-09-07 | 2022-09-09 | Defining Problem Statement | C | B | 2 | 300 | 600 | 100 | 600 | C | 600 | 600 | 600 | 2 | 5 | 7 | 5 | 7 | 0 | Yes | Yes
Proposal Documentation | Shruti Shetty, Shreya Shetty | Medium | Done | 2022-09-10 | 2022-09-11 | Defining Objectives and Features, Defining Problem Statement | D | B,C | 1 | 200 | 200 | 100 | 300 | D | 300 | 200 | 200 | 1 | 7 | 8 | 7 | 8 | 0 | Yes | Yes
Project Proposal Approval | Shreya Shetty, Shruti Shetty | Low | Done | 2022-09-12 | 2022-09-13 | Proposal Documentation | E | D | 1 | 500 | 500 | 100 | 400 | E | 400 | 500 | 500 | 1 | 8 | 9 | 8 | 9 | 0 | Yes | Yes
|  |  |  | 2022-08-31 | 2022-09-13 |  |  |  | 9 | 2100 | 3900 | 500 | 3800 | 0 | 3800 | 3900 | 3900 | 9 | 24 | 33 | 24 | 33 | 0 |  | 0
Phase II
Name | Person | Priority | Status | Timeline - Start | Timeline - End | Dependency | Activity Node Name | Predecessor | Duration | Cost/Day | Total Cost | Actual Complete | Incurred Cost | Activity Node | ACWP | BCWP | BCWS | Today-End | Early Start | Early Finish | Late Start | Late Finish | Slack | Critical Path | Is Slack == 0?
Designing UI | Shreya Shetty | High | Planned | 2022-09-13 | 2022-09-20 | Project Proposal Approval | F | E | 7 | 1000 | 7000 | 100 | 6000 | F | 6000 | 7000 | 7000 | 7 | 9 | 16 | 9 | 16 | 0 | Yes | Yes
Database connectivity and setup | Shruti Shetty | Medium | Planned | 2022-09-21 | 2022-09-23 | Designing UI | G | F | 2 | 500 | 1000 | 90 | 1100 | G | 1100 | 900 | 1000 | 2 | 16 | 18 | 18 | 20 | 2 | No | No
Login-Signup Implementation | Shruti Shetty | Low | Planned | 2022-09-24 | 2022-09-26 | Designing UI, Database connectivity and setup | H | F, G | 2 | 500 | 1000 | 80 | 800 | H | 800 | 800 | 1000 | 2 | 16 | 18 | 20 | 22 | 4 | No | No
Implementation of User System | Shruti Shetty | High | Planned | 2022-09-27 | 2022-10-03 | Login-Signup Implementation | I | H | 6 | 200 | 1200 | 60 | 1000 | I | 1000 | 720 | 1200 | 6 | 18 | 24 | 22 | 28 | 4 | No | No
Implementation of Property System | Shreya Shetty | High | Planned | 2022-10-04 | 2022-10-10 | Designing UI | J | F | 6 | 300 | 1800 | 80 | 900 | J | 900 | 1440 | 1800 | 6 | 16 | 22 | 16 | 22 | 0 | Yes | Yes
Implementation of Booking System | Shreya Shetty | High | Planned | 2022-10-11 | 2022-10-17 | Implementation of Property System | K | J | 6 | 400 | 2400 | 50 | 1000 | K | 1000 | 1200 | 2400 | 6 | 22 | 28 | 22 | 28 | 0 | Yes | Yes
Phase II Documentation and Presentation | Shreya Shetty, Shruti Shetty | Low | Planned | 2022-10-18 | 2022-10-19 | Implementation of Booking System, Implementation of User System | L | I, K | 1 | 1000 | 1000 | 5 | 100 | L | 100 | 50 | 1000 | 1 | 28 | 29 | 28 | 29 | 0 | Yes | Yes
|  |  |  | 2022-09-13 | 2022-10-19 |  |  |  | 30 | 3900 | 15400 | 465 | 10900 | 0 | 10900 | 12110 | 15400 | 30 | 125 | 155 | 135 | 165 | 10 |  | 0
Phase III
Name | Person | Priority | Status | Timeline - Start | Timeline - End | Dependency | Activity Node Name | Predecessor | Duration | Cost/Day | Total Cost | Actual Complete | Incurred Cost | Activity Node | ACWP | BCWP | BCWS | Today-End | Early Start | Early Finish | Late Start | Late Finish | Slack | Critical Path | Is Slack == 0?
Implementation of Payment System | Shreya Shetty | Medium | Planned | 2022-10-20 | 2022-10-28 | Phase II Documentation and Presentation | M | L | 8 | 500 | 4000 | 20 | 700 | M | 700 | 800 | 4000 | 8 | 29 | 37 | 29 | 37 | 0 | Yes | Yes
Implementation of Inventory Management | Shruti Shetty | High | Planned | 2022-10-29 | 2022-11-07 | Implementation of Payment System | N | M | 9 | 500 | 4500 | 20 | 500 | N | 500 | 900 | 2000 | 4 | 37 | 46 | 37 | 46 | 0 | Yes | Yes
Testing | Shreya Shetty | Medium | Planned | 2022-11-08 | 2022-11-14 | Implementation of Inventory Management, Implementation of Payment System | O | M, N | 6 | 300 | 1800 | 0 | 0 | O | 0 | 0 | 0 | 0 | 46 | 52 | 46 | 52 | 0 | Yes | Yes
Deployment | Shruti Shetty | High | Planned | 2022-11-15 | 2022-11-23 | Testing | P | O | 8 | 600 | 4800 | 0 | 0 | P | 0 | 0 | 0 | 0 | 52 | 60 | 52 | 60 | 0 | Yes | Yes
Phase III Documentation | Shreya Shetty, Shruti Shetty | Medium | Planned | 2022-11-24 | 2022-11-29 | Deployment, Testing | Q | O, P | 5 | 500 | 2500 | 0 | 0 | Q | 0 | 0 | 0 | 0 | 60 | 65 | 60 | 65 | 0 | Yes | Yes
Final Project Report Preparation | Shreya Shetty, Shruti Shetty | High | Planned | 2022-11-30 | 2022-12-06 | Phase III Documentation | R | Q | 6 | 1000 | 6000 | 0 | 0 | R | 0 | 0 | 0 | 0 | 65 | 71 | 65 | 71 | 0 | Yes | Yes
Final Presentation |  | Default |  | 2022-12-07 | 2022-12-13 | Final Project Report Preparation | S | R | 6 | 100 | 600 | 0 | 0 | S | 0 | 0 | 0 | 0 | 71 | 77 | 71 | 77 | 0 | Yes | Yes
|  |  |  | 2022-10-20 | 2022-12-13 |  |  |  | 48 | 3500 | 24200 | 40 | 1200 | 0 | 1200 | 1700 | 6000 | 12 | 360 | 408 | 360 | 408 | 0 |  | 0
[15 empty] | ACWP | BCWP | BCWS
[14 empty] | TOTAL SUM | 15900 | 17710 | 25300
[14 empty] | CPI | CV | SPI | SV
[14 empty] | 1.1138 | 1810 | 0.7 | -7590